## Sheet1
Task Name | Start Date | Duration (Days)
Phase 1: Ontology Development | 2024-07-01 | 10
Define Geometric Concepts | 2024-07-01 | 4
Develop Ontology in Protégé | 2024-07-05 | 6
Phase 2: System Development | 2024-07-11 | 21
Design System Architecture | 2024-07-11 | 5
Develop User Interface | 2024-07-16 | 7
Implement Feedback Mechanism | 2024-07-23 | 6
Integrate Ontology with System | 2024-07-29 | 3
Phase 3: Testing and Evaluation | 2024-08-01 | 15
Conduct User Testing | 2024-08-01 | 8
Collect Feedback and Analyze Results | 2024-08-09 | 4
Modify and Fine-Tune the System | 2024-08-13 | 3